## Sheet1
PROJECT X - Automated Attendace System
Task ID | Task Name | Sub Task ID | Sub Task Name | Deliverables | Estimated Hours | Assignee | Start Date | End Date | Status | Actual Hours Spent | Notes
1 | Project Initiation | 1.1 | Requirements Gathering | Requirements Document | 5 | Richard Fuertes | 2025-02-27 | 2025-02-28 | Done | 2
|  | 1.2 | Feasibility Study | Feasibility Report | 8 | Rudilito Dongiapon Jr. | 2025-03-01 | 2025-03-03 | Done | 2
|  | 1.3 | Stakeholder Analysis | Stakeholder Report | 6 | Jhon Ryan Pagantian | 2025-02-03 | 2025-03-04 | Done | 3
|  | 1.4 | Risk Assessment & Mitigation | Risk Analysis Report | 7 | Cristian Villanueva | 2025-03-05 | 2025-03-05 | Done | 2
|  | 1.5 | Project Planning & Timeline | Project Plan, Timeline | 8 | Rudilito Dongiapon Jr. | 2025-03-07 | 2025-03-08 | Done | 3
|  | 1.6 | Approval & Kickoff Meeting | Meeting Minutes, Approval Doc | 5 | Cristian Villanueva | 2025-03-10 | 2025-03-11 | Done | 3
2 | System Design | 2.1 | Database Schema Design | ER Diagram, Schema Scripts | 8 | Rudilito Dongiapon Jr. | 2025-03-13 | 2025-03-18 | Done | 4
|  | 2.2 | UI/UX Wireframes & Prototypes | Wireframes, UI Mockups | 10 | Frances Al Capiña | 2025-03-18 | 2025-03-19 | Done | 4
|  | 2.3 | System Architecture Design | Architecture Diagram | 8 | Jhon Ryan Pagantian | 2025-03-18 | 2025-03-19 | Done | 5
|  | 2.4 | API Design & Documentation | API Documentation | 8 | Frances Al Capiña | 2025-03-19 | 2025-03-20 | Done | 6
|  | 2.5 | Technology Stack Finalization | Tech Stack Document | 6 | Rudilito Dongiapon Jr. | 2025-03-20 | 2025-03-20 | Done | 4
|  | 2.6 | Security & Compliance Planning | Security Compliance Document | 7 | Cristian Villanueva | 2025-03-21 | 2025-03-21 | Done | 8
3 | Development | 3.1 | Frontend - Login & Dashboard | UI Components | 10 | Rudilito Dongiapon Jr. | 2025-03-21 | 2025-03-22 | Done | 9
|  | 3.2 | Frontend - Attendance Interface | Attendance UI | 9 | Frances Al Capiña | 2025-03-22 | 2025-03-22 | Done | 9
|  | 3.3 | Backend - Authentication | User Authentication API | 8 | Jhon Ryan Pagantian | 2025-03-22 | 2025-03-23 | Done | 7
|  | 3.4 | Backend - Attendance Logic | Attendance Tracking API | 10 | Frances Al Capiña | 2025-03-23 | 2025-03-24 | Done | 6
|  | 3.5 | Database Integration | Functional Database | 10 | Cristian Villanueva | 2025-03-24 | 2025-03-24 | Done | 9
|  | 3.6 | RFID/Biometric Integration | Functional Attendance System | 15 | Jhon Ryan Pagantian | 2025-03-25 | 2025-03-25 | Done | 12
|  | 3.7 | Role-Based Access Control | Authentication System | 10 | Cristian Villanueva | 2025-03-25 | 2025-03-26 | Done | 9
|  | 3.8 | Notification System (Email/SMS) | Notification Module | 10 | Rudilito Dongiapon Jr. | 2025-03-26 | 2025-03-26 | Pending
4 | Testing | 4.1 | Unit Testing | Test Cases, Bug Reports | 8 | Cristian Villanueva | 2025-03-26 | 2025-03-26 | Done | 12
|  | 4.2 | Integration Testing | Integration Test Report | 10 | Jhon Ryan Pagantian | 2025-03-26 | 2025-03-27 | Done | 9
|  | 4.3 | User Acceptance Testing (UAT) | UAT Feedback Report | 8 | Rudilito Dongiapon Jr. | 2025-03-27 | 2025-03-27 | Done | 6
5 | Deployment | 5.1 | Deployment to Staging | Staging Environment Setup | 8 | Frances Al Capiña | 2025-03-27 | 2025-03-28 | Pending
|  | 5.2 | Production Deployment | Live System | 10 | Jhon Ryan Pagantian | 2025-03-28 | 2025-03-29 | Pending
|  | 5.3 | Training & Documentation | User Guide, Training Sessions | 12 | Cristian Villanueva | 2025-03-29 | 2025-03-30 | Pending
6 | Maintenance | 6.1 | Bug Fixes & Minor Updates | Patch Releases | 7 | Rudilito Dongiapon Jr. | 2025-04-01 | 2025-04-03 | Pending
|  | 6.2 | Security & Monitoring | Security Patches, Logs | 10 | Jhon Ryan Pagantian | 2025-04-03 | 2025-04-08 | Pending